Mattersey and Mattersey Thorpe Neighbourhood Plan

Notes from the meeting on 3rd January 2017

Chair : Bob Kendall agreed to chair the meeting

Apologies : None

Present :  Parish Councillors, the Parish Clerk, Helen Metcalfe (Consultant)  and 9 residents.

Notes from the last meeting were agreed.

The meeting was handed over to Helen, we had asked her for a timeline for completion of the N. Plan process, and what work we needed to do to achieve this.

Helen needs completed Vision and Objectives with policy and supporting evidence.

Obtain the Scoping report from James at BDC by half term.

Email Rural Community Profile to Helen and the group.

Ask Joelle Davies for the Site Assessments, email to Helen by half term.

Ask Joelle about the progress with the Landowners, ? when the report will be ready.

Housing Needs Assessment, ACON report should be ready very soon , Adele will chase it. When it is done and reviewed by the group a discussion may be needed with BDC re : relevance.

A further consultation will be needed when we know the sites that the landowners are willing to put forward for development, then those sites can be put in order of preference by the villagers.

Helen would like to do a sites visit, Bob will accompany Helen on February 1st

Put in Idle Talk that there will be an upcoming consultation event possibly in February.

A meeting to be arranged for March 7th to discuss V1 and comments to Helen by 9th March

Ask Joelle for guidelines and criteria for the Sustainability Appraisal

Send Helen’s Timeline to all N. Plan contacts.

UPDATES

Comments for Vision and sites were discussed earlier.

Weebly, some people couldn’t download the questionnaire, advised to delete the pdf version and see if that helps.

Student’s questionnaire, Tony will look at any response this week.

Everton, ask if they would like to attend a meeting on 31st January, asking if they have any issues that have been raised that may affect Mattersey/ Thorpe or vice versa.

Social network, Weebly has been fairly quiet over Christmas

Facebook, we still need to get it transferred over to Alice

Arrange a meeting with Joelle Davies preferably 17th January

Any other business  -  It was agreed that the Neighbourhood Plan Group should sent comments in on each planning application as well as from the P. Council.

Funding has now come through

Date and time of the next meeting      17th January 7pm in the Church Hall